## Cover
ORANGE HRM TEST DESIGN
Project Name | ORANGE HRM TEST DESIGN |  | Project Code |  | Version | 1
Creator | Giáp Minh Luật -SE04780 |  | Position | Tester | Date | 2019-10-10
Reviewer | Nguyễn Thị Hương - SE04846 |  | Position | Tester | Date | 2018-11-20
Approver | Vũ Ngọc Thưởng - SE04786 |  | Position | Tester | Date | 2018-12-15
Record of change
Effective Date | Version | Changed Sheet | *A, D, M | Change description |  | Author
2019-10-10 | 1.0 | All sheets | A | First create |  | LuatGM
Introduction
Sheet Name |  | Description |  |  | Note
Cover |  | Title page and Introduction |  |  | This page
Reference |  | - List of reference documents that the Test plan is based on. - List of Terminologies and definition/explanation
Test Strategy |  | Description of Test strategy, test scope and types, test environment, acceptance criteria
Test Management |  | Information about test planning and management: - Master schedule - Deliverables of test project - Management method - Risks - Constraints - Assumptions - Training plan
Requirement |  | List of Requirements
List of TC |  | Description of Test case structure, number of TC, TC classification, …
Note on A8: QuynhHN: Effective Date must be after approve date
Note on D8: *A: Add M: Modify D: Delete

## References
Reference
Reference Document
# | Title/File name | Author | Version | Effective Date | Note
1 | SoftwareTestingHelp_OrangeHRM_FRS.docx | http://www.SoftwareTestingHelp.com
Term definition
# | Term | Definition/explanation
1 | GUI | Graphic User Interface
2 | PM | Project Manager
3 | TC | Test Case
4 | TP | Test Plan
5 | TR | Test Report
6 | UI | User Interface
7 | UT | Unit test
8 | ST | System test

## Test Strategy
Test Strategy
Test scope | Test scope |  |  | Doer |  | Defect Plan | Note
| þ | System test |  | Tester | Tester | 10
Test types | Test Type |  |  | Technique | Completion Criteria
| þ | Functionality | Functionality | Manual/automatic | All test cases have been executed. All identified defects have been closed
| þ | Interfaces | Interfaces | Manual/automatic | Each GUI is successfully verified
| þ | Regression | Regression | Manual/automatic | - 80% Test cases is randomly select - All test cases are implemented and passed
| Software |  | - Window 10 - Google Chrome
| Platform |  | Real Machine
Start standard | 1 | System test is starts only when UT is passed by UT Inspection
| 2 | System test is starts only when The necessary hardware/software is available
End standard | 1 | UT is only finished if the defects which is detect in Final unit test inspection is closed
| 2 | ST is only finished if all defects must have to closed and all ST testcase is executed
Acceptance criteria | # | Criteria |  | Unit | Target | Note
| 1 | Test coverage |  | % | 100
| 2 | Successful Test coverage |  | % | 100
| 3 | Number of Unit Test cases | # | Case | 300
| 4 | Number of review defects | # | Case | 10
| 5 | Rate of valid TC | % | % | 60
| 6 | Rate of invalid TC | % | % | 30
| 7 | Rate of boundary TC | % | % | 10
Note on A3: Select items by change □ to ■
Note on G3: Planned Defect number for each Test level
Note on A5: Select items by change □ to ■
Note on E5: - Manual - Test tool ….
Note on A11: Condition to start testing
Note on A13: Condition to finish testing

## Test Management
Test Management
| # | Major activity | Start date | End date | Person in charge | Note
| 1 | Study Specs | 2019-10-01 | 2019-10-10 | LuatGM,HuongNT,ThuongVN
| 2 | Create Test plan | 2019-10-10 | 2019-10-10 | LuatGM
| 3 | Create Test design (TD) | 2019-10-10 | 2019-10-10 | LuatGM
| 4 | Review & update TD | 2019-10-11 | 2019-10-11 | LuatGM
| 5 | Create Test case | 2019-10-11 | 2019-10-11 | LuatGM,HuongNT
| 6 | Review & update TC | 2019-10-12 | 2019-10-13 | LuatGM,HuongNT
| 7 | Create Test data | 2019-10-12 | 2019-10-13 | LuatGM,HuongNT
|  | Update TC | 2019-10-12 | 2019-10-13 | LuatGM,HuongNT
|  | Review UT spec | 2019-10-12 | 2019-10-13 | LuatGM,HuongNT
| 8 | Do UT Inspection | 2019-10-15 | 2019-10-15 | ThuongVN
Deliverables | 9 | Execute test | 2019-11-01 | 2019-12-05 | Another Team
| 10 | Evaluate test result | 2019-12-15 | 2019-12-15 | Another Team
| # | Deliverables | Delivered date | Delivered by | Delivered to | Note
| 1 | Test plan | 2019-12-15 | LuatGM | ThuongVN
| 2 | Test design (Test summary) | 2019-12-15 | LuatGM | ThuongVN
Management method | 3 | Test cases | 2019-12-15 | LuatGM | ThuongVN
| 4 | Test data | 2019-12-15 | LuatGM | ThuongVN
| 5 | Test report | 2019-12-15 | LuatGM | ThuongVN
| 6 | Create user manual | 2019-12-15 | LuatGM | ThuongVN
Risks | # | Condition | Mitigation | Contigency | Doer | Assessed Date
| 1 | The hardware maybe corrupt when testing | Using hardware carefully | Re-Plan schedule | LuatGM | 2019-12-15
| 2 | Software trail maybe expired | Complete test within 30 days trail | Regist new trail at Orange HRM | LuatGM | 2019-12-15
| 3 | Time for testing may is not enough | Add more resource to implement testing | Note cases which can't implement in test report | HuongNT,ThuongVN | 2019-12-15
| 4 | Unit test is not goot or have not enough time to implement unit test | Push PM to team do unit test correct with schedule | Add more resource to implement testing | LuatGM | 2019-12-15
Constraint | # | Description |  |  |  | Type
| 1 | Test environment: Test environment is built like the actual environment.
| 2 | Software is provided by OrangeHRM
Assumption | # | Description |  |  |  | Type
| 2 | Board hardware works well
Note on A23: List all risks which can occur and impact to test activities
Note on C23: Describe the existing condition that could possibly lead to a risk of testing. (Điều kiện có thể dẫn đến việc xảy ra risk)
Note on E23: Actions to eliminate the probability of the occurrence. (Hành động để phòng ngừa, ngăn không cho risk xảy ra)
Note on F23: Action to reduce negative impacts when the risk occurs. Hành động chữa cháy, để giảm thiểu thiệt hại khi risk xảy ra.
Note on G23: Persons who are responsible for mitigation and Contigency action
Note on H23: Date to check whether the risk can be closed or not
Note on A28: List any constraints on products provided by other teams, resource, schedule, test tools, etc
Note on H28: It can be: - Requirement - Test Products - Test environment - Test tools ...
Note on A31: List any assumptions made during the testing
Note on H31: It can be: - Requirement - Test Products - Test environment - Test tools ...

## Requirement
List of Requirements
Requirements to be tested:
| # | Test Items |  | Note
| 1 | Contact Details module
| 2 | Emergency Contacts module
| 3 | Job module
| 4 | Salary module
| 5 | Qualifications module
Acceptance criteria
| # | Criteria |  | Unit | Target | Note
| 1 | Test coverage | Functionality | % | 100
| 2 | Successful Test coverage | Interfaces | % | 100
| 3 | Number of Unit Test cases | Load and Stress | case | 300
| 4 | Number of review defects | Recovery | % | 30
Note on C5: Major features and functions to be tested

## List Of TC
LIST OF TEST CASES
| Number of test case: | 342
Module | Large item | No | Medium Item | Implement | Expected number of TC |  |  |  |  | Doer | Note
[5 empty] | Normal | Abnormal | Boundary | Regression test | Total
Sprint1 | Login,Logout | 1 |  |  | 3 | 2 |  |  | 5
| Employee Quantity | 2 |  |  | 2 | 0 |  |  | 2
| Employee managent | 3 |  |  | 20 | 4 |  |  | 24
| Termination of contract | 4 |  |  | 6 | 3 |  |  | 9
Sprint2 | Tranfers | 5 |  |  | 27 | 2 |  |  | 29
| Brief managent | 6 | Brief inside company |  | 20 | 7 |  |  | 27
|  | 7 | Brief outside company |  | 14 | 2 |  |  | 16
|  | 8 | Regulation |  | 73 | 10 |  |  | 83
Sprint3 | Certificate | 9 |  |  | 21 | 4 |  |  | 25
| Degree-DaskCertificate | 10 |  |  | 25 | 8 |  |  | 33
Sprint4 | Salary | 11 |  |  | 21 | 4 |  |  | 25
| Occupation | 12 |  |  | 24 | 4 |  |  | 28
Sprint5 | Asign Task | 13 |  |  | 10 | 2 |  |  | 12
| Take Attendance | 14 |  |  | 20 | 4 |  |  | 24
|  | 5 | 3 | 0 | 5 | 5 | 0 |  | 342
Note on A6: Module/Function will be tested. It's normally a sheet in Test case document
Note on B6: Module/Function will be tested. It's large item in TC
Note on D6: Define content which we implement to test in a module. It's medium item in TC
Note on E6: Implement or not: - Y/ N or - X/blank
Note on K6: Tester who will test the module/function/item
Note on F7: Normally 60% of all TC
Note on G7: Normally 30% of all TC
Note on H7: Normally 10% of all TC